## Legal Requirements
Category | Requirement | Authority | Required Documents | Start Date | Target Date | Processing Time | Responsible | Status | Notes
Registration | GAFI Investment Registration | General Authority for Investment | Business Plan, Founders ID, Residence Proof | 2026-08-01 | 2026-08-30 | 7-14 days | Legal Officer | Not Started | Critical path item - required before MOH application
Healthcare License | Ministry of Health Facility License | Ministry of Health & Population | License Application, Facility Plans, Clinical Protocols, Staff Credentials, Floor Plans | 2026-08-15 | 2026-10-15 | 30-60 days | Healthcare Compliance | Not Started | CRITICAL - Must be obtained before soft opening
Tax Compliance | Egyptian Tax Authority Registration | Egyptian Tax Authority (ETA) | Tax ID Application, Business Registration, Identification Documents | 2026-08-15 | 2026-09-15 | 10-15 days | Finance Manager | Not Started | Prerequisite for VAT registration
Tax Compliance | VAT Registration | Egyptian Tax Authority (ETA) | VAT Registration Application, Tax ID, Business Details | 2026-09-01 | 2026-09-30 | 10-15 days | Finance Manager | Not Started | Required for billing and accounting
Municipal | Giza Governorate Zoning Approval | Giza Governorate Authority | Zoning Application, Facility Location Map, Building Plans | 2026-08-15 | 2026-09-30 | 15-30 days | Facilities Manager | Not Started | Required before construction can begin
Municipal | Building Construction Permit | Giza Governorate Building Authority | Building Permit Application, Architectural Drawings, Engineer Approval | 2026-08-20 | 2026-10-15 | 20-40 days | Facilities Manager | Not Started | Needed for renovation/construction activities
Safety & Civil Defense | Fire Safety Certification | Egyptian Civil Defense Authority | Fire Safety Plan, Emergency Procedures, Floor Plans, Inspection Reports | 2026-09-15 | 2026-10-30 | 20-40 days | Safety Officer | Not Started | CRITICAL - Required before facility operations
Safety & Civil Defense | Emergency Evacuation Procedures Approval | Egyptian Civil Defense Authority | Evacuation Plan, Drill Procedures, Staff Training Records | 2026-10-01 | 2026-11-15 | 30-45 days | Safety Officer | Not Started | Must be integrated with MOH requirements
Environmental | Medical Waste Management Approval | Egyptian Environmental Affairs Agency | Waste Management Plan, Treatment Method Details, Contractor Agreement | 2026-09-15 | 2026-11-15 | 20-45 days | EHS Officer | Not Started | Must identify licensed waste management contractor
Insurance | Professional Liability Insurance | Licensed Insurance Companies | Insurance Policy, Coverage Certificate, Premium Proof | 2026-09-01 | 2026-10-01 | 7-14 days | Risk Manager | Not Started | Minimum coverage recommended: 1M EGP
Insurance | General Liability Insurance | Licensed Insurance Companies | Insurance Policy, Coverage Certificate, Premium Proof | 2026-09-01 | 2026-10-01 | 7-14 days | Risk Manager | Not Started | Property and operations coverage
Employment | Social Insurance Fund (SIF) Registration | Social Insurance Fund | Employee Registration Forms, Contracts, Identification Documents | 2026-11-01 | 2026-11-30 | 5-10 days per employee | HR Manager | Not Started | Must be done for all employees before start
Professional Licenses | Egyptian Medical Syndicate Registration | Egyptian Medical Syndicate | License Verification, Educational Credentials, Professional Certificates | 2026-11-01 | 2027-01-31 | 10-20 days | HR Manager | Not Started | CRITICAL for all clinical staff - required before patient care
Data Protection | Data Privacy Compliance (Law 151/2020) | Ministry of Communications & IT | Privacy Policy, Data Protection Plan, IT Security Measures | 2026-09-01 | 2026-10-15 | Ongoing | Data Protection Officer | Not Started | Continuous compliance throughout operations
Patient Records | Clinical Documentation System Approval | Ministry of Health & Population | EMR System Details, Security Protocols, Audit Trails | 2026-12-01 | 2027-02-28 | 15-30 days | Clinical Ops Manager | Not Started | Ensure MOH compliance for all documentation