## Master Schedule
Task ID | Task Name | Description | Start Date | End Date | Duration (days) | Dependencies | Priority | Responsible | Status
T1.1 | Project Initiation & Planning | Establish governance, scope, team | 2026-07-30 | 2026-08-15 | 16 | None | CRITICAL | Project Director | Not Started
T1.2 | Company Registration (GAFI) | Register with General Authority for Investment | 2026-08-01 | 2026-08-30 | 30 | T1.1 | CRITICAL | Legal Officer | Not Started
T1.3 | Healthcare Licensing - MOH | Ministry of Health facility license application | 2026-08-15 | 2026-10-15 | 61 | T1.2 | CRITICAL | Healthcare Compliance | Not Started
T1.4 | Tax Registration & VAT | ETA registration, VAT setup | 2026-08-15 | 2026-09-15 | 31 | T1.2 | HIGH | Finance Manager | Not Started
T1.5 | Municipality Approval (Giza) | Zoning approval, building permits | 2026-08-15 | 2026-09-30 | 46 | T1.2 | HIGH | Facilities Manager | Not Started
T1.6 | Civil Defense & Fire Safety | Fire safety certification, emergency procedures | 2026-09-15 | 2026-10-30 | 45 | T1.5 | CRITICAL | Safety Officer | Not Started
T1.7 | Environmental & Waste Approval | Medical waste management, environmental approval | 2026-09-15 | 2026-11-15 | 61 | T1.3 | HIGH | EHS Officer | Not Started
T1.8 | Insurance Policies | Professional & general liability insurance | 2026-09-01 | 2026-10-01 | 30 | T1.1 | HIGH | Risk Manager | Not Started
T1.9 | Data Privacy Compliance | Patient data protection, Law 151/2020 | 2026-09-01 | 2026-10-15 | 44 | T1.1 | HIGH | Data Protection Officer | Not Started
T2.1 | Facility Site Selection | Identify and lease New Cairo facility | 2026-07-30 | 2026-09-15 | 48 | T1.5 | CRITICAL | Facilities Manager | Not Started
T2.2 | Architectural Design | Develop architectural and MEP drawings | 2026-08-01 | 2026-09-30 | 60 | T2.1 | CRITICAL | Facilities Manager | Not Started
T2.3 | Interior Design | Design therapy rooms, reception, waiting areas | 2026-08-15 | 2026-09-30 | 46 | T2.2 | HIGH | Facilities Manager | Not Started
T2.4 | Construction & Renovation | Execute all construction, installations | 2026-10-01 | 2027-01-31 | 122 | T2.2, T2.3 | CRITICAL | Construction Manager | Not Started
T2.5 | Furniture Installation | Procure and install all furniture | 2026-11-15 | 2027-02-28 | 105 | T2.4 | HIGH | Procurement Manager | Not Started
T2.6 | Medical Equipment | Procurement and installation of therapy equipment | 2026-10-15 | 2027-03-31 | 168 | T2.1 | CRITICAL | Clinical Equipment Mgr | Not Started
T2.7 | IT Infrastructure | Servers, network, WiFi, cameras, access control | 2026-11-01 | 2027-02-28 | 119 | T2.4 | HIGH | IT Manager | Not Started
T2.8 | Signage & Branding | Install signage, clinic branding, reception setup | 2027-02-01 | 2027-03-15 | 42 | T2.4, T2.5 | MEDIUM | Branding Manager | Not Started
T2.9 | Final Inspections | MOH, Civil Defense, Municipality final approvals | 2027-02-28 | 2027-03-31 | 31 | T2.4, T2.6, T2.7 | CRITICAL | Compliance Officer | Not Started
T3.1 | Clinical Workflow Design | Patient journey, workflows, documentation | 2026-09-01 | 2026-10-31 | 60 | T1.1 | HIGH | Clinical Director | Not Started
T3.2 | Department Structure | Define OT, PT, Speech, Psychology departments | 2026-09-15 | 2026-11-15 | 61 | T3.1 | HIGH | Clinical Director | Not Started
T3.3 | Quality & Infection Control | QA programs, infection control, safety | 2026-10-01 | 2026-12-15 | 76 | T3.2 | CRITICAL | Quality & Safety Mgr | Not Started
T3.4 | Patient Consent & Docs | Consent forms, documentation templates | 2026-10-15 | 2026-12-01 | 47 | T1.9, T3.1 | HIGH | Clinical Ops Mgr | Not Started
T3.5 | Appointment & Billing | Configure clinic management and billing systems | 2026-11-15 | 2027-01-31 | 78 | T2.7 | HIGH | Ops & IT Manager | Not Started
T3.6 | Emergency Procedures | Emergency protocols, evacuation, disaster plans | 2026-11-01 | 2026-12-31 | 60 | T1.6, T3.3 | CRITICAL | Safety Manager | Not Started
T4.1 | Organization Structure | Define organizational structure and roles | 2026-09-01 | 2026-09-30 | 30 | T1.1 | HIGH | HR Manager | Not Started
T4.2 | Job Descriptions | Create job descriptions for all positions | 2026-09-15 | 2026-10-31 | 46 | T4.1 | HIGH | HR Manager | Not Started
T4.3 | Clinical Staff Recruitment Tier 1 | Recruit Director, Clinical Director, Heads | 2026-09-15 | 2026-11-30 | 76 | T4.2 | CRITICAL | HR Manager | Not Started
T4.4 | Clinical Staff Recruitment Tier 2 | Recruit therapists (OT, PT, Speech, Psych) | 2026-10-15 | 2026-12-31 | 77 | T4.3 | CRITICAL | HR Manager | Not Started
T4.5 | Admin & Support Staff | Recruit reception, admin, cleaning, security | 2026-11-01 | 2027-01-31 | 92 | T4.2 | HIGH | HR Manager | Not Started
T4.6 | License Verification | Verify staff licenses, Medical Syndicate registration | 2026-11-01 | 2027-01-31 | 92 | T4.4 | CRITICAL | HR Manager | Not Started
T4.7 | Employment Contracts | Prepare contracts, health insurance, payroll | 2026-11-01 | 2027-02-28 | 119 | T4.5 | HIGH | HR Manager | Not Started
T4.8 | Staff Orientation | Comprehensive orientation and onboarding | 2027-01-15 | 2027-03-15 | 59 | T4.5, T4.7 | HIGH | HR Manager | Not Started
T4.9 | Clinical Training | Clinical protocols, system training, competency | 2027-02-01 | 2027-04-05 | 63 | T4.8, T3.2 | CRITICAL | Clinical Director | Not Started
T5.1 | Technology Requirements | Define tech requirements, select systems | 2026-10-01 | 2026-11-15 | 45 | T1.1, T3.5 | HIGH | IT Manager | Not Started
T5.2 | EMR Implementation | Implement Electronic Medical Records system | 2026-11-01 | 2027-02-28 | 119 | T5.1, T2.7 | CRITICAL | IT Manager | Not Started
T5.3 | Billing & Accounting | Configure billing system and accounting software | 2026-12-01 | 2027-02-28 | 90 | T5.1 | HIGH | Finance & IT Mgr | Not Started
T5.4 | CRM Implementation | Implement CRM for patient management | 2027-01-01 | 2027-03-15 | 73 | T5.1 | MEDIUM | IT & Ops Mgr | Not Started
T5.5 | Cybersecurity Setup | Cybersecurity, data backup, disaster recovery | 2027-01-01 | 2027-03-31 | 89 | T2.7, T5.2 | CRITICAL | IT Manager | Not Started
T6.1 | Marketing Strategy | Develop marketing strategy and campaigns | 2026-12-01 | 2027-01-31 | 61 | T1.1 | HIGH | Marketing Manager | Not Started
T6.2 | Digital Presence | Launch website, social media, online booking | 2027-01-01 | 2027-02-28 | 59 | T2.8, T5.4 | HIGH | Marketing Manager | Not Started
T6.3 | Pre-Launch Marketing | Advertising, PR, partnerships pre-opening | 2027-02-01 | 2027-03-31 | 58 | T6.1, T6.2 | HIGH | Marketing Manager | Not Started
T6.4 | Soft Opening | Soft opening for internal testing | 2027-03-01 | 2027-03-31 | 31 | T2.9, T4.9, T5.2 | CRITICAL | Clinical Director | Not Started
T6.5 | Grand Opening Prep | Final marketing, VIP invitations, media | 2027-04-01 | 2027-05-06 | 35 | T6.4 | HIGH | Marketing Manager | Not Started
T6.6 | GRAND OPENING | Official clinic grand opening | 2027-05-06 | 2027-05-06 | 1 | T6.5, T2.9 | CRITICAL | Project Director | Not Started
T7.1 | Final Readiness Audit | Comprehensive pre-opening readiness assessment | 2027-04-06 | 2027-05-06 | 30 | T6.4 | CRITICAL | Project Manager | Not Started
T7.2 | Operations Manual | Complete operations manual and policies | 2027-02-01 | 2027-03-31 | 58 | T3.2, T4.2 | HIGH | Ops Manager | Not Started
T7.3 | EMR Testing | Full EMR and documentation system testing | 2027-03-01 | 2027-03-31 | 31 | T5.2, T3.4 | CRITICAL | Clinical Ops Mgr | Not Started
T7.4 | Patient Scheduling | Activate patient scheduling and confirmations | 2027-04-01 | 2027-05-06 | 35 | T5.3, T6.3 | HIGH | Ops Manager | Not Started

## Milestones
Milestone | Target Date | Status | Responsible
Company Registration Complete | 2026-08-30 | Not Started | Legal Officer
Healthcare Licensing Received | 2026-10-15 | Not Started | Healthcare Compliance
All Approvals Complete | 2026-11-15 | Not Started | Compliance Officer
Facility Construction Complete | 2027-01-31 | Not Started | Construction Manager
Medical Equipment Installed | 2027-03-31 | Not Started | Clinical Equipment Mgr
All Staff Trained & Ready | 2027-02-28 | Not Started | Clinical Director
Technology Systems Go-Live | 2027-02-28 | Not Started | IT Manager
Soft Opening (Testing Phase) | 2027-03-31 | Not Started | Clinical Director
GRAND OPENING | 2027-05-06 | Not Started | Project Director

## Critical Path
Sequence | Task | Duration | Status
1 | Project Initiation | 16 | Not Started
2 | Company Registration | 30 | Not Started
3 | Healthcare Licensing | 61 | Not Started
4 | Facility Selection | 48 | Not Started
5 | Architectural Design | 60 | Not Started
6 | Construction & Renovation | 122 | Not Started
7 | Medical Equipment | 168 | Not Started
8 | Clinical Staff Recruitment & Training | 169 | Not Started
9 | Technology Implementation | 119 | Not Started
10 | Final Inspections | 31 | Not Started
11 | Soft Opening | 31 | Not Started
12 | Grand Opening | 1 | Not Started