TRIAD THERAPEUTIC CLINIC

PROJECT IMPLEMENTATION PLAN

New Cairo, Egypt

Rehabilitation Center Establishment

Project Timeline: July 30, 2026 - May 6, 2027 (Grand Opening)

Document Version: 1.0 - Professional Project Management Office (PMO) Deliverable

EXECUTIVE SUMMARY

Project Scope

This Master Project Implementation Plan outlines the complete establishment of TRIAD Therapeutic Clinic, a multidisciplinary rehabilitation center in New Cairo, Egypt. The project encompasses legal registration, facility development, clinical operations setup, technology infrastructure, human resources development, and market entry across a 10-month timeline.

Project Objectives

• Achieve Soft Opening in March 2027 with internal testing and controlled patient admission

• Execute Grand Opening on May 6, 2027 with full clinical operations and public launch

• Secure all Egyptian healthcare licenses and regulatory approvals

• Establish world-class clinical operations with Egyptian standards compliance

• Recruit and train 25+ clinical and support staff

• Implement integrated technology systems for patient care and operations

Critical Path Summary

The critical path includes: Company Registration → Healthcare Licensing → Facility Preparation → Medical Equipment Procurement → Clinical Staff Recruitment & Training → System Implementation → Soft Opening → Grand Opening.

Key Milestones

| Milestone | Target Date |
| --- | --- |
| Company & Healthcare Licensing Complete | October 2026 |
| Facility Construction Complete | January 2027 |
| Clinical Staff Fully Trained & Ready | February 2027 |
| Technology Systems Go-Live | March 2027 |
| Soft Opening (Internal Testing) | March 2027 |
| GRAND OPENING | May 6, 2027 |

1. MASTER PROJECT TIMELINE

Complete Task Listing with Dependencies (Extract follows on supporting Excel schedule)

| Task ID | Task Name | Duration | Priority | Responsible |
| --- | --- | --- | --- | --- |
| T1.1 | Project Initiation & Planning | 16d | CRITICAL | Project Director |
| T1.2 | Company Registration (Egyptian Authority) | 30d | CRITICAL | Legal & Compliance Officer |
| T1.3 | Healthcare Licensing Application - MOH | 61d | CRITICAL | Healthcare Compliance Manager |
| T1.4 | Tax Registration & Compliance Setup | 31d | HIGH | Finance Manager |
| T1.5 | Municipality Approval (Giza Governorate) | 46d | HIGH | Facilities Manager |
| T1.6 | Civil Defense & Fire Safety Approval | 45d | CRITICAL | Safety & Compliance Officer |
| T1.7 | Environmental & Waste Management Approval | 61d | HIGH | Environmental Health & Safety Officer |
| T1.8 | Insurance Policies & Coverage | 30d | HIGH | Risk Manager |
| T1.9 | Data Privacy & GDPR-Equivalent Compliance | 44d | HIGH | Data Protection Officer |
| T2.1 | Facility Site Selection & Lease Execution | 48d | CRITICAL | Facilities Manager |

... [Complete task list continues in supporting Excel file] ...

2. LEGAL & GOVERNMENT REQUIREMENTS (EGYPT)

Required Egyptian Healthcare & Business Licensing

| Category | Requirement | Authority | Processing Time |
| --- | --- | --- | --- |
| Company Registration | General Authority for Investment (GAFI) Registration | General Authority for Investment (GAFI) | 7-14 days |
| Healthcare Licensing | Ministry of Health & Population (MOH) Facility License | Ministry of Health & Population | 30-60 days |
| Tax Compliance | Egyptian Tax Authority (ETA) Registration & VAT | Egyptian Tax Authority (ETA) | 10-15 days |
| Municipality Approval | Giza Governorate Zoning & Building Permit | Giza Governorate Building Authority | 15-30 days |
| Civil Defense | Fire Safety & Emergency Procedures Certification | Egyptian Civil Defense Authority | 20-40 days |
| Environmental | Medical Waste Management & Environmental Compliance | Egyptian Environmental Affairs Agency | 20-45 days |
| Insurance | Professional Liability & General Liability Insurance | Licensed Insurance Companies | 7-14 days |
| Employment | Employee Registration with Social Insurance Fund (SIF) | Social Insurance Fund (SIF) | 5-10 days |
| Professional Licenses | Egyptian Medical Syndicate Registration for Clinical Staff | Egyptian Medical Syndicate | 10-20 days |
| Data Protection | Patient Data Privacy Compliance (Law 151/2020) | Ministry of Communications & IT | Ongoing Compliance |

Critical Notes: All licenses must be obtained before Soft Opening. Healthcare licensing is the critical path item and should be prioritized immediately.

DETAILED SECTIONS CONTINUE:

3. Facility Preparation Plan (detailed in supporting documents)

4. Clinical Operations Setup (detailed in supporting documents)

5. Human Resources Structure & Hiring Plan (detailed in supporting documents)

6. Finance & Procurement Plan (detailed in supporting documents)

7. Documentation Library & Checklist (detailed in supporting documents)

8. Marketing & Launch Plan (detailed in supporting documents)

9. Technology Systems Implementation (detailed in supporting documents)

10. Risk Management & Contingency Planning (detailed in supporting documents)

11. Opening Readiness Checklists (detailed in supporting documents)

12. Project Dashboard & Reporting (detailed in supporting documents)

All supporting documents are maintained in organized folder structure:

/Project_Documents/English/ - All English language documents

/Project_Documents/Arabic/ - All Arabic language documents

Document prepared as PMO-level project implementation resource. All supporting schedules, templates, checklists, and forms follow in structured Excel and Word documents.